## in
Issue Type | Issue key | Issue id | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due date
Epic | CP-2 | 10004 | Implement Main Menu |  | Zack McGill | Medium | Done |  | 2025-08-24 01:47 | 2025-08-24 01:47
Epic | CP-5 | 10033 | All Reports |  | Zack McGill | Medium | Done |  | 2025-09-08 17:17 | 2025-10-08 03:28
Epic | CP-6 | 10034 | Project Proposal and Presentable Elements |  | Zack McGill | Medium | Done | Done | 2025-09-08 17:18 | 2025-09-22 17:12
Story | CP-8 | 10036 | Refine PP for Proposal Presentation |  | Zack McGill | Medium | Done | Done | 2025-09-08 17:20 | 2025-09-22 17:11 | 2025-09-18
Story | CP-110 | 10416 | Commission character art | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-11-04 13:31 | 2026-01-14 12:45
Story | CP-65 | 10204 | Woodwind puzzle |  | Steven LaGoy | Lowest | To Do |  | 2025-10-06 17:27 | 2026-02-10 21:12
Epic | CP-11 | 10039 | Settings Menu |  | Zack McGill | Medium | Done |  | 2025-09-08 17:39 | 2025-09-08 17:39
Epic | CP-16 | 10044 | World Layout |  | Zack McGill | Medium | Done |  | 2025-09-08 18:00 | 2025-09-08 18:00
Epic | CP-17 | 10045 | Adding Assets to World Layout |  | Zack McGill | Medium | Done |  | 2025-09-08 18:01 | 2025-09-08 18:01
Epic | CP-18 | 10046 | Lighting and Atmosphere |  | Zack McGill | Medium | Done |  | 2025-09-08 18:01 | 2025-09-08 18:01
Epic | CP-19 | 10047 | Creating the Player |  | Zack McGill | Medium | Done |  | 2025-09-08 18:04 | 2025-09-08 18:04
Epic | CP-20 | 10048 | Game Mechanics |  | Zack McGill | Medium | Done |  | 2025-09-08 18:04 | 2025-09-08 18:04
Epic | CP-21 | 10049 | Texturing World Layout |  | Zack McGill | Medium | Done |  | 2025-09-08 18:09 | 2025-09-08 18:09
Story | CP-23 | 10051 | Make a Sketch of the World Layout | Ricardo Saldana | Zack McGill | Medium | Done | Done | 2025-09-08 18:12 | 2025-09-22 17:42
Story | CP-26 | 10054 | Presentation of Assets Fitting our Games Look | Harrison Niswander | Zack McGill | Medium | Done | Done | 2025-09-08 18:21 | 2025-09-12 15:07
Story | CP-24 | 10052 | Sketch out a Story Plan | Steven LaGoy | Zack McGill | Medium | Done | Done | 2025-09-08 18:15 | 2025-09-22 17:09
Story | CP-7 | 10035 | PowerPoint for Proposal and Sponsor | Logan Faulstich | Zack McGill | Medium | Done | Done | 2025-09-08 17:19 | 2025-09-15 16:03 | 2025-09-12
Story | CP-27 | 10055 | Visually Present our Tech Stack and Workflow | Zack McGill | Zack McGill | Medium | Done | Done | 2025-09-08 18:22 | 2025-09-22 17:09
Story | CP-25 | 10053 | Visually Present Ideas for Puzzles | Riley Tate | Zack McGill | Medium | Done | Done | 2025-09-08 18:15 | 2025-09-15 16:08
Epic | CP-28 | 10056 | Music |  | Steven LaGoy | Medium | Done |  | 2025-09-08 18:49 | 2025-09-08 18:49
Story | CP-35 | 10070 | Ambient Music | Steven LaGoy | Steven LaGoy | Lowest | To Do |  | 2025-09-08 18:51 | 2026-02-10 21:12
Story | CP-36 | 10072 | Central Area Music | Steven LaGoy | Steven LaGoy | Medium | To Do |  | 2025-09-08 18:52 | 2026-01-26 00:10
Subtask | CP-37 | 10100 | Gather renders with camera behind player model. | Ricardo Saldana | Ricardo Saldana | Medium | Done | Done | 2025-09-10 13:30 | 2025-09-11 13:08
Subtask | CP-38 | 10102 | Upload finalized blender files. | Ricardo Saldana | Ricardo Saldana | Medium | Done | Done | 2025-09-10 13:32 | 2025-09-18 23:14
Subtask | CP-39 | 10104 | Gather reference footage from A Short Hike / The Witness / Resonance of the Ocean / It Takes Two. | Ricardo Saldana | Ricardo Saldana | Medium | Done | Done | 2025-09-10 13:34 | 2025-09-22 17:42
Epic | CP-44 | 10137 | Preliminary Report |  | Steven LaGoy | Medium | Done |  | 2025-09-22 17:21 | 2025-09-22 17:22 | 2025-10-10
Story | CP-51 | 10148 | Collect asset packs | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2025-09-22 17:33 | 2025-10-01 13:14
Story | CP-52 | 10149 | Formalize puzzle designs | Riley Tate | Steven LaGoy | Medium | Done | Done | 2025-09-22 17:33 | 2025-10-05 18:17
Story | CP-49 | 10146 | Basic player movement / camera | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-09-22 17:28 | 2026-01-15 19:16
Task | CP-42 | 10134 | Create Unreal project | Steven LaGoy | Steven LaGoy | High | Done | Done | 2025-09-22 17:15 | 2026-01-15 19:16
Task | CP-57 | 10157 | Sign and submit Project Proposal Document |  | Steven LaGoy | High | Done | Done | 2025-09-22 21:34 | 2025-09-29 22:36 | 2025-09-26
Story | CP-48 | 10145 | Risk Assessment Document | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2025-09-22 17:23 | 2025-10-01 13:14
Story | CP-56 | 10156 | Meet with Prof. Bolinger about report requirements | Steven LaGoy | Steven LaGoy | High | Done | Done | 2025-09-22 18:05 | 2025-09-29 22:36
Story | CP-43 | 10136 | Ocean and rough island terrain | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-09-22 17:18 | 2025-09-29 22:36
Story | CP-78 | 10217 | Player movement demo | Zack McGill | Steven LaGoy | Highest | Done | Done | 2025-10-10 00:21 | 2025-10-22 12:05 | 2025-10-17
Story | CP-81 | 10231 | Midterm presentation |  | Steven LaGoy | Highest | Done | Done | 2025-10-10 14:51 | 2025-10-27 13:39 | 2025-10-24
Story | CP-40 | 10132 | Team name and logo design | Logan Faulstich | Steven LaGoy | Low | Done | Done | 2025-09-22 17:11 | 2025-10-02 15:47
Story | CP-77 | 10216 | Color mechanic demo | Harrison Niswander | Steven LaGoy | Highest | Done | Done | 2025-10-10 00:20 | 2025-12-13 23:34 | 2025-12-14
Story | CP-97 | 10401 | Settings Screen | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2025-11-03 18:13 | 2025-12-04 16:45
Story | CP-71 | 10210 | Technical Story Bible | Ricardo Saldana | Ricardo Saldana | Medium | Done | Done | 2025-10-06 21:41 | 2025-10-29 23:56
Story | CP-45 | 10139 | Vision Document | Ricardo Saldana | Steven LaGoy | High | Done | Done | 2025-09-22 17:22 | 2025-10-10 00:27 | 2025-10-10
Story | CP-41 | 10133 | Finish Perforce setup | Zack McGill | Steven LaGoy | Highest | Done | Done | 2025-09-22 17:15 | 2025-10-22 12:03
Story | CP-50 | 10147 | Concept art for areas | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2025-09-22 17:31 | 2025-10-12 21:39
Story | CP-79 | 10218 | Game map tour | Steven LaGoy | Steven LaGoy | Highest | Done | Done | 2025-10-10 00:22 | 2025-10-22 12:02 | 2025-10-17
Story | CP-46 | 10141 | Requirements Model | Riley Tate | Steven LaGoy | High | Done | Done | 2025-09-22 17:22 | 2025-10-10 00:27 | 2025-10-10
Story | CP-59 | 10198 | Woodwind area foliage | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2025-10-06 17:26 | 2025-10-22 12:02
Story | CP-47 | 10143 | Project Plan + Milestones | Ricardo Saldana | Steven LaGoy | High | Done | Done | 2025-09-22 17:23 | 2025-10-10 00:27 | 2025-10-10
Subtask | CP-54 | 10152 | Formalize vision for area biomes |  | Steven LaGoy | Medium | Done | Done | 2025-09-22 17:47 | 2025-10-22 12:04
Subtask | CP-55 | 10154 | Connect areas nature to instrument themes |  | Steven LaGoy | Medium | Done | Done | 2025-09-22 17:47 | 2025-10-22 12:03
Story | CP-58 | 10165 | Add Unreal project to Perforce VCS |  | Steven LaGoy | Highest | Done | Done | 2025-09-29 22:36 | 2025-09-29 22:37
Story | CP-4 | 10006 | Design and Implement Splash Screen | Logan Faulstich | Zack McGill | Medium | Done | Done | 2025-08-24 01:58 | 2025-10-29 11:23
Story | CP-53 | 10150 | Finish storywriting | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2025-09-22 17:41 | 2025-10-29 12:08
Story | CP-80 | 10219 | Story bible MVP | Ricardo Saldana | Steven LaGoy | Highest | Done | Done | 2025-10-10 00:22 | 2025-10-29 12:08 | 2025-10-17
Story | CP-93 | 10334 | Recover SharePoint | Logan Faulstich | Steven LaGoy | Highest | Done | Done | 2025-10-22 12:32 | 2025-10-29 12:08
Story | CP-114 | 10487 | Design a cutscene for completing crystal puzzle | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2025-11-12 12:58 | 2025-12-01 18:42
Story | CP-109 | 10415 | Make islands and bridges appear or move | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-11-03 19:00 | 2025-12-01 18:42
Story | CP-120 | 10525 | Camera work for cutscene | Ricardo Saldana | Zack McGill | Medium | Done | Done | 2025-11-19 13:34 | 2025-12-01 18:42
Story | CP-67 | 10206 | Keys puzzle |  | Steven LaGoy | Highest | Done | Done | 2025-10-06 17:27 | 2025-12-01 18:41
Story | CP-62 | 10201 | Percussion area foliage | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-10-06 17:27 | 2025-11-19 13:28
Task | CP-116 | 10521 | Scale default player model |  | Steven LaGoy | Medium | Done | Done | 2025-11-19 12:41 | 2025-11-19 13:28
Story | CP-117 | 10522 | Populate Cave foliage / textures | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2025-11-19 12:41 | 2025-11-19 13:28
Story | CP-63 | 10202 | Keys area foliage | Steven LaGoy | Steven LaGoy | Highest | Done | Done | 2025-10-06 17:27 | 2025-11-19 13:29
Story | CP-119 | 10524 | Moving doors and bridge | Steven LaGoy | Zack McGill | Medium | Done | Done | 2025-11-19 13:34 | 2025-11-22 02:01
Story | CP-121 | 10526 | Rumbling noise and door open noise | Steven LaGoy | Zack McGill | Medium | Done | Done | 2025-11-19 13:35 | 2025-11-22 02:01
Story | CP-124 | 10529 | Puzzle logic for simon says | Riley Tate | Zack McGill | Medium | Done | Done | 2025-11-19 13:36 | 2025-11-22 02:01
Story | CP-123 | 10528 | Implement fail mechanic, play noise, reset counter 0, light up red matching fail noise | Riley Tate | Zack McGill | Medium | Done | Done | 2025-11-19 13:35 | 2025-11-22 02:01
Story | CP-128 | 10565 | Keys area ambient music | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-11-21 14:10 | 2025-12-01 18:41
Story | CP-122 | 10527 | Refine light up of pads as well as tie in lighting up the crystals | Zack McGill | Zack McGill | Medium | Done | Done | 2025-11-19 13:35 | 2025-12-03 17:20
Story | CP-75 | 10214 | Complete Preliminary Report | Steven LaGoy | Steven LaGoy | High | Done | Done | 2025-10-10 00:18 | 2025-10-10 00:18 | 2025-10-10
Story | CP-69 | 10208 | Create cave in mountain | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-10-06 17:28 | 2025-10-10 00:24
Story | CP-76 | 10215 | 1 Puzzle MVP |  | Steven LaGoy | Highest | Done | Done | 2025-10-10 00:19 | 2026-01-14 12:30 | 2025-12-14
Story | CP-82 | 10264 | Walls / Barriers between areas | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-10-12 21:32 | 2025-10-12 21:38
Story | CP-72 | 10211 | Reorganize SharePoint Site | Ricardo Saldana | Steven LaGoy | Low | Done | Done | 2025-10-07 23:07 | 2025-10-12 21:37
Story | CP-85 | 10267 | Ocean and Beach foliage | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-10-15 02:18 | 2025-10-15 02:18
Story | CP-74 | 10213 | Make rivers in Brass Area | Steven LaGoy | Steven LaGoy | High | Done | Done | 2025-10-08 12:51 | 2025-10-16 01:03
Story | CP-60 | 10199 | Brass area foliage | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-10-06 17:26 | 2025-10-16 01:03
Story | CP-84 | 10266 | Make a basic main menu | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2025-10-12 21:40 | 2025-10-29 23:56
Story | CP-92 | 10333 | Prepare client update |  | Steven LaGoy | Medium | Done | Done | 2025-10-22 12:08 | 2025-11-03 17:32
Story | CP-73 | 10212 | Set up budget | Harrison Niswander | Steven LaGoy | Highest | Done | Done | 2025-10-07 23:08 | 2025-12-03 17:23
Story | CP-34 | 10068 | Keys Area Music | Steven LaGoy | Steven LaGoy | High | Done | Done | 2025-09-08 18:51 | 2025-11-11 22:39
Story | CP-94 | 10366 | Finalize logo designs | Logan Faulstich | Steven LaGoy | Highest | Done | Done | 2025-10-29 12:09 | 2025-11-11 22:39
Story | CP-96 | 10400 | Pause Screen | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2025-11-03 18:13 | 2025-11-17 19:14
Story | CP-83 | 10265 | Choose assets to use as foliage |  | Steven LaGoy | Medium | Done | Done | 2025-10-12 21:38 | 2025-11-11 22:40
Story | CP-70 | 10209 | Design basic UI elements | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2025-10-06 17:31 | 2025-11-12 13:04
Story | CP-108 | 10414 | Make passages between areas | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-11-03 18:58 | 2025-11-17 17:25
Story | CP-115 | 10488 | Correct hitboxes | Zack McGill | Steven LaGoy | Medium | Done | Done | 2025-11-12 13:14 | 2025-11-19 13:12
Subtask | CP-87 | 10302 | Make logo design printable |  | Steven LaGoy | Medium | Done | Done | 2025-10-16 01:05 | 2025-12-03 17:23
Subtask | CP-88 | 10304 | Find screen printing or digital printing shop |  | Steven LaGoy | Medium | Done | Done | 2025-10-16 01:05 | 2025-12-03 17:23
Subtask | CP-91 | 10310 | Get team member shirt sizes |  | Steven LaGoy | Medium | Done | Done | 2025-10-16 01:06 | 2025-12-03 17:23
Subtask | CP-89 | 10306 | Get the shirts printed |  | Steven LaGoy | Medium | Done | Done | 2025-10-16 01:05 | 2026-01-12 19:06
Subtask | CP-90 | 10308 | Give the shirts to team members |  | Steven LaGoy | Medium | Done | Done | 2025-10-16 01:05 | 2026-01-12 19:06
Subtask | CP-95 | 10399 | Get Player to pick up and drop bucket |  | Riley Tate | Medium | To Do |  | 2025-11-03 18:12 | 2025-11-04 15:07
Subtask | CP-98 | 10402 | Allow Bucket to fill with water |  | Riley Tate | Medium | To Do |  | 2025-11-03 18:13 | 2025-11-03 18:13
Subtask | CP-99 | 10403 | Create holes to be filled with water |  | Riley Tate | Medium | To Do |  | 2025-11-03 18:14 | 2025-11-03 18:14
Subtask | CP-100 | 10404 | Create goal state and way to tell user what to do |  | Riley Tate | Medium | To Do |  | 2025-11-03 18:19 | 2025-11-03 18:19
Subtask | CP-101 | 10405 | Create way to see if the puzzle is complete |  | Riley Tate | Medium | Done |  | 2025-11-03 18:22 | 2025-11-03 18:22
Subtask | CP-102 | 10406 | Sculpt cave and add more crystals | Ricardo Saldana | Riley Tate | Medium | Done | Done | 2025-11-03 18:40 | 2025-12-03 17:21
Subtask | CP-104 | 10408 | Add button crystals for the player to step on | Riley Tate | Riley Tate | Medium | Done | Done | 2025-11-03 18:43 | 2025-11-12 13:19
Subtask | CP-103 | 10407 | Add display crystals that show pattern |  | Riley Tate | Medium | Done | Done | 2025-11-03 18:42 | 2025-11-24 13:34
Subtask | CP-106 | 10411 | Make crystals change color on trigger | Riley Tate | Steven LaGoy | Medium | Done | Done | 2025-11-03 18:56 | 2025-11-19 13:43
Subtask | CP-111 | 10450 | Get triggers or events to communicate with different elements of puzzle | Riley Tate | Steven LaGoy | Medium | Done | Done | 2025-11-05 13:15 | 2025-11-18 15:59
Subtask | CP-107 | 10413 | Make a sound play on trigger | Riley Tate | Steven LaGoy | Medium | Done | Done | 2025-11-03 18:56 | 2025-11-16 21:56
Subtask | CP-112 | 10452 | Track sequence of player note input | Riley Tate | Steven LaGoy | Medium | Done | Done | 2025-11-05 13:16 | 2025-11-17 17:29
Subtask | CP-113 | 10454 | Track success / failure of round and puzzle | Riley Tate | Steven LaGoy | Medium | Done | Done | 2025-11-05 13:16 | 2025-11-17 17:28
Subtask | CP-105 | 10409 | Create music and sounds for the puzzle | Steven LaGoy | Riley Tate | Medium | Done | Done | 2025-11-03 18:44 | 2025-12-03 17:21
Task | CP-131 | 10568 | Final presentation |  | Steven LaGoy | Medium | Done | Done | 2025-11-21 14:14 | 2025-12-12 22:28 | 2025-12-12
Story | CP-86 | 10300 | Make team tee shirts | Zack McGill | Steven LaGoy | Medium | Done | Done | 2025-10-16 01:04 | 2025-12-10 11:23
Story | CP-125 | 10530 | Add additional events to winnings | Zack McGill | Zack McGill | Medium | Done | Done | 2025-11-19 13:36 | 2025-12-10 11:23
Story | CP-130 | 10567 | Final presentation PowerPoint |  | Steven LaGoy | Highest | Done | Done | 2025-11-21 14:14 | 2025-12-12 22:27 | 2025-12-10
Story | CP-134 | 10603 | Enable color for ocean and sky | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2025-12-03 17:26 | 2025-12-03 17:26
Story | CP-135 | 10604 | Enable color for specific assets | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2025-12-03 17:26 | 2025-12-03 17:26
Story | CP-133 | 10602 | Fix doors |  | Steven LaGoy | Medium | Done | Done | 2025-12-03 17:25 | 2025-12-08 18:57
Story | CP-61 | 10200 | Strings area foliage | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-10-06 17:26 | 2025-12-08 18:57
Story | CP-132 | 10601 | Add purchased assets to content folders |  | Steven LaGoy | Medium | Done | Done | 2025-12-03 17:25 | 2025-12-08 18:57
Story | CP-9 | 10037 | Create extensible NPC blueprint | Steven LaGoy | Zack McGill | High | Done | Done | 2025-09-08 17:35 | 2026-04-08 12:54
Story | CP-261 | 11258 | Innovation Day Poster |  | Steven LaGoy | Medium | Done | Done | 2026-04-08 13:01 | 2026-04-08 17:32 | 2026-04-08
Story | CP-223 | 11152 | Play testing |  | Steven LaGoy | Highest | Done | Done | 2026-03-25 13:59 | 2026-04-18 21:00
Story | CP-30 | 10060 | Brass Area Music | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-09-08 18:50 | 2026-04-18 21:00
Story | CP-251 | 11216 | Fix settings menu in packaged game builds |  | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:53 | 2026-04-18 21:00
Story | CP-222 | 11151 | Player sounds | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2026-03-25 13:58 | 2026-04-20 14:21
Story | CP-226 | 11155 | Color areas based on puzzle completion | Riley Tate | Steven LaGoy | Medium | Done | Done | 2026-03-25 14:07 | 2026-04-20 14:22
Story | CP-259 | 11256 | NPCs | Riley Tate | Steven LaGoy | Medium | Done | Done | 2026-04-08 12:54 | 2026-04-18 21:01
Story | CP-177 | 10831 | Dialog system | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-02-10 21:14 | 2026-04-18 21:01
Story | CP-189 | 10910 | Particles | Ricardo Saldana | Steven LaGoy | Low | Done | Done | 2026-02-24 23:56 | 2026-04-20 16:35
Story | CP-188 | 10909 | Ambient sounds | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:56 | 2026-04-20 16:35
Story | CP-272 | 11305 | Add labels and locks to bridges | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-13 14:38 | 2026-04-20 16:35
Story | CP-260 | 11257 | Interact prompt for unlocking passages with notes | Zack McGill | Steven LaGoy | Highest | Done | Done | 2026-04-08 12:56 | 2026-04-20 16:35
Story | CP-193 | 10914 | Team Lobster Brass puzzle 1 | Zack McGill | Steven LaGoy | Highest | Done | Done | 2026-02-24 23:57 | 2026-04-20 16:37
Story | CP-29 | 10058 | Compose Game Theme Music | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-09-08 18:50 | 2026-04-20 16:37
Task | CP-244 | 11205 | Add button prompts | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:51 | 2026-04-20 16:37
Story | CP-149 | 10655 | Strings puzzle team krill 2 | Harrison Niswander | Steven LaGoy | High | Done | Done | 2026-01-14 14:34 | 2026-03-20 22:32
Story | CP-66 | 10205 | Strings puzzle team krill 1 | Riley Tate | Steven LaGoy | High | Done | Done | 2025-10-06 17:27 | 2026-03-20 22:32
Story | CP-68 | 10207 | Percussion puzzle team shrimp 1 | Ricardo Saldana | Steven LaGoy | High | Done | Done | 2025-10-06 17:28 | 2026-03-20 22:32
Story | CP-217 | 11082 | Feedback Analysis Report |  | Steven LaGoy | Highest | Done | Done | 2026-03-02 20:12 | 2026-03-20 22:32
Story | CP-33 | 10066 | Percussion Area Music | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-09-08 18:51 | 2026-03-01 02:41
Story | CP-185 | 10906 | Game installer / launcher | Zack McGill | Steven LaGoy | Lowest | Done | Done | 2026-02-24 23:55 | 2026-03-20 22:32
Story | CP-187 | 10908 | Test out character model | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:56 | 2026-03-20 22:32
Story | CP-202 | 10962 | Create RTM for strings puzzle | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2026-02-25 13:56 | 2026-03-20 22:32
Story | CP-205 | 10965 | Complete testing of Keys puzzle | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-02-25 13:57 | 2026-03-20 22:32
Story | CP-207 | 10967 | Testing of Percussion puzzle | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2026-02-25 13:58 | 2026-03-20 22:32
Story | CP-12 | 10040 | Implement Saving and Loading | Riley Tate | Zack McGill | Highest | Done | Done | 2025-09-08 17:39 | 2026-03-16 13:53
Story | CP-142 | 10646 | Exploration challenges | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-14 13:31 | 2026-03-01 02:41
Story | CP-140 | 10644 | Remake forest area to be Percussion | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-01-14 12:32 | 2026-03-01 02:42
Story | CP-184 | 10905 | Create game executable | Zack McGill | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:55 | 2026-03-16 13:53
Story | CP-148 | 10654 | Remake forest area to be Percussion 2 | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2026-01-14 14:32 | 2026-03-01 02:42
Story | CP-190 | 10911 | Water movement interaction | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:56 | 2026-03-16 13:53
Task | CP-174 | 10796 | Fix the bridges and moving islands | Steven LaGoy | Steven LaGoy | Highest | Done | Done | 2026-01-28 13:32 | 2026-03-02 19:16
Story | CP-32 | 10064 | Strings Area Music | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-09-08 18:51 | 2026-01-26 00:10
Story | CP-118 | 10523 | Allow an area to be put in full color | Zack McGill | Zack McGill | Medium | Done | Done | 2025-11-19 13:33 | 2026-02-09 14:18
Task | CP-150 | 10688 | Fix jungle tree collisions |  | Steven LaGoy | Medium | Done | Done | 2026-01-25 23:52 | 2026-02-09 14:18
Task | CP-151 | 10689 | Fix nighttime ambient lighting |  | Steven LaGoy | Medium | Done | Done | 2026-01-25 23:52 | 2026-02-10 20:57
Story | CP-139 | 10643 | Build castle | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-14 12:29 | 2026-02-10 21:10
Story | CP-147 | 10653 | Percussion puzzle team shrimp 2 | Logan Faulstich | Steven LaGoy | High | Done | Done | 2026-01-14 14:32 | 2026-03-14 19:40
Story | CP-224 | 11153 | Strings puzzle polish | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2026-03-25 13:59 | 2026-04-27 14:02
Story | CP-220 | 11149 | New cutscenes 1 | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-03-25 13:57 | 2026-05-02 12:36
Story | CP-231 | 11160 | New cutscenes 2 | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2026-03-25 14:45 | 2026-05-02 12:36
Story | CP-262 | 11259 | Cinematic Trailer | Steven LaGoy | Steven LaGoy | High | Done | Done | 2026-04-08 13:01 | 2026-04-28 14:02 | 2026-04-17
Story | CP-273 | 11338 | Music for tutorial | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-20 14:46 | 2026-05-02 12:36
Story | CP-64 | 10203 | Brass puzzle polish | Zack McGill | Steven LaGoy | Highest | Done | Done | 2025-10-06 17:27 | 2026-05-02 12:36
Story | CP-225 | 11154 | Percussion puzzle polish | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-03-25 13:59 | 2026-05-02 12:36
Story | CP-274 | 11339 | New Game button on main menu | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-20 14:47 | 2026-05-02 12:36
Story | CP-221 | 11150 | Door opening interaction |  | Steven LaGoy | Medium | Done | Done | 2026-03-25 13:57 | 2026-04-28 14:02
Story | CP-271 | 11304 | Add locks and note numbers to other sides of doors | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-13 13:49 | 2026-05-02 12:35
Story | CP-176 | 10830 | Keybind settings | Logan Faulstich | Steven LaGoy | Highest | Done | Done | 2026-02-10 21:02 | 2026-04-28 14:02
Story | CP-268 | 11269 | Keybind settings | Zack McGill | Steven LaGoy | Medium | Done | Done | 2026-04-08 17:34 | 2026-04-28 14:02
Story | CP-275 | 11340 | Keybind settings | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-20 16:35 | 2026-04-28 14:02
Story | CP-276 | 11373 | Test bridges for puzzle completion | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-22 14:00 | 2026-04-28 14:02
Story | CP-269 | 11270 | Volume settings | Zack McGill | Steven LaGoy | Medium | Done | Done | 2026-04-08 17:34 | 2026-04-28 14:02
Story | CP-179 | 10833 | Collectable system | Steven LaGoy | Steven LaGoy | High | Done | Done | 2026-02-10 21:39 | 2026-02-11 14:34
Task | CP-173 | 10795 | Fix Nanite shadowmap error | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-28 13:24 | 2026-02-21 20:57
Task | CP-175 | 10829 | Fix memory budget exceeded warning | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-02-10 21:00 | 2026-02-21 20:57
Story | CP-180 | 10866 | Player camera tweaks | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-02-16 14:02 | 2026-02-21 21:14
Story | CP-143 | 10647 | Collection challenges | Steven LaGoy | Steven LaGoy | Lowest | Done | Done | 2026-01-14 13:31 | 2026-02-24 23:50
Subtask | CP-146 | 10652 | Documentation | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-01-14 14:18 | 2026-01-26 00:11
Subtask | CP-152 | 10691 | Race 1: Lap around the whole island |  | Steven LaGoy | Medium | Done | Done | 2026-01-25 23:56 | 2026-03-25 13:34
Subtask | CP-153 | 10693 | Race 2: Jungle area loop |  | Steven LaGoy | Medium | Done | Done | 2026-01-25 23:56 | 2026-03-25 13:34
Subtask | CP-154 | 10695 | Race 3: Brass area loop |  | Steven LaGoy | Medium | Done | Done | 2026-01-25 23:56 | 2026-04-08 12:48
Subtask | CP-155 | 10697 | Race 4: Woodwind castle town relay |  | Steven LaGoy | Medium | Done | Done | 2026-01-25 23:56 | 2026-04-08 12:48
Subtask | CP-156 | 10699 | Collection 1: Note fragments |  | Steven LaGoy | Medium | Done | Done | 2026-01-25 23:59 | 2026-02-25 17:24
Subtask | CP-157 | 10701 | Collection 2 |  | Steven LaGoy | Medium | Done | Done | 2026-01-26 | 2026-02-25 17:24
Subtask | CP-158 | 10703 | Parkour 1: Island hopping |  | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:03 | 2026-02-15 21:59
Subtask | CP-159 | 10705 | Parkour 2: Castle climb |  | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:04 | 2026-04-08 12:47
Subtask | CP-160 | 10707 | Parkour 3: Mountain climb |  | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:04 | 2026-03-02 19:52
Subtask | CP-161 | 10709 | Exploration 1: Brass bridges puzzle |  | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:05 | 2026-03-25 13:35
Subtask | CP-162 | 10711 | Exploration 2: Visit all areas |  | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:07 | 2026-03-25 13:35
Subtask | CP-165 | 10717 | Main Menu | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:13 | 2026-02-10 21:02
Subtask | CP-163 | 10713 | Load Game menu | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:13 | 2026-04-08 12:46
Subtask | CP-164 | 10715 | New Game menu | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:13 | 2026-04-08 12:46
Subtask | CP-166 | 10719 | Pause Screen | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:13 | 2026-02-10 21:02
Subtask | CP-145 | 10650 | Unstuck Button | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-14 14:18 | 2026-04-08 12:46
Subtask | CP-167 | 10721 | Settings menu | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:13 | 2026-02-10 21:02
Subtask | CP-137 | 10608 | Mouse sensitivity | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-12-03 17:28 | 2026-04-08 12:46
Subtask | CP-136 | 10606 | Keymapping capability | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2025-12-03 17:27 | 2026-01-26 00:15
Subtask | CP-138 | 10610 | FOV setting | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2025-12-03 17:28 | 2026-04-08 12:46
Subtask | CP-168 | 10723 | Invert y-axis setting | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:14 | 2026-04-08 12:46
Subtask | CP-169 | 10725 | Resolution settings | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:14 | 2026-04-08 12:46
Subtask | CP-170 | 10727 | Framerate settings | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:14 | 2026-04-08 12:46
Subtask | CP-171 | 10729 | Audio settings | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-26 00:14 | 2026-04-08 12:46
Story | CP-31 | 10062 | Woodwind Area Music | Steven LaGoy | Steven LaGoy | Low | To Do |  | 2025-09-08 18:50 | 2026-04-23 12:38
Story | CP-252 | 11217 | Add signs and pointers around the world to different areas |  | Steven LaGoy | Medium | To Do |  | 2026-04-01 15:53 | 2026-05-02 12:36
Subtask | CP-178 | 10832 | UI Scale setting |  | Steven LaGoy | Medium | Done | Done | 2026-02-10 21:26 | 2026-04-08 12:46
Subtask | CP-181 | 10868 | Move camera closer to player, over shoulder |  | Steven LaGoy | Medium | Done | Done | 2026-02-16 14:04 | 2026-02-21 21:11
Subtask | CP-182 | 10870 | Investigate alternate approaches to objects blocking the camera |  | Steven LaGoy | Medium | Done | Done | 2026-02-16 14:05 | 2026-02-21 21:14
Subtask | CP-183 | 10872 | Add crosshair |  | Steven LaGoy | Medium | Done | Done | 2026-02-16 14:05 | 2026-02-21 21:15
Story | CP-192 | 10913 | Create RTM for percussion puzzle | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:57 | 2026-03-13 23:48
Story | CP-206 | 10966 | Testing of Strings puzzle | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2026-02-25 13:58 | 2026-03-13 23:48
Story | CP-204 | 10964 | Improve feel of interactables | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2026-02-25 13:57 | 2026-03-16 13:53
Story | CP-191 | 10912 | Initial minimal player testing | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:56 | 2026-03-16 13:53
Story | CP-186 | 10907 | Adjust player jump distance and speed | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:55 | 2026-03-16 13:53
Subtask | CP-195 | 10917 | Complete definition |  | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:58 | 2026-04-23 12:37
Subtask | CP-196 | 10919 | Remake brass area for puzzle | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:58 | 2026-03-01 02:42
Subtask | CP-197 | 10921 | Cameras | Zack McGill | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:59 | 2026-04-23 12:37
Subtask | CP-198 | 10923 | Input method | Zack McGill | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:59 | 2026-04-23 12:37
Subtask | CP-199 | 10925 | Floating objects mechanic | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:59 | 2026-03-01 19:32
Subtask | CP-200 | 10927 | Valve / direction mechanic | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:59 | 2026-03-02 01:45
Subtask | CP-201 | 10929 | Sounds | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-02-24 23:59 | 2026-04-23 12:37
Subtask | CP-208 | 11001 | Spawning and despawning floating objects | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-03-01 17:28 | 2026-03-18 15:58
Subtask | CP-209 | 11003 | Pathing for objects | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-03-01 17:28 | 2026-03-02 01:45
Subtask | CP-210 | 11005 | Game overlay / UI | Zack McGill | Steven LaGoy | Medium | Done | Done | 2026-03-01 17:31 | 2026-04-23 12:37
Subtask | CP-211 | 11007 | Create valves | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-03-01 17:31 | 2026-03-01 19:32
Subtask | CP-212 | 11009 | Win and lose conditions | Zack McGill | Steven LaGoy | Medium | Done | Done | 2026-03-01 17:32 | 2026-04-23 12:37
Subtask | CP-213 | 11011 | Interaction to begin game | Zack McGill | Steven LaGoy | Medium | Done | Done | 2026-03-01 17:32 | 2026-04-23 12:37
Subtask | CP-214 | 11013 | Object path splines | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-03-01 17:35 | 2026-03-02 01:45
Subtask | CP-215 | 11015 | Tutorial |  | Steven LaGoy | Medium | Done | Done | 2026-03-01 17:50 | 2026-04-23 12:37
Subtask | CP-216 | 11049 | Parkour 4: Town dock |  | Steven LaGoy | Medium | Done | Done | 2026-03-02 01:47 | 2026-03-02 01:47
Story | CP-172 | 10762 | Inventory system | Steven LaGoy | Steven LaGoy | Low | Done | Done | 2026-01-26 14:30 | 2026-03-25 14:11
Story | CP-194 | 10915 | Team Lobster Brass puzzle 2 | Steven LaGoy | Steven LaGoy | Highest | Done | Done | 2026-02-24 23:57 | 2026-03-25 14:00
Story | CP-227 | 11156 | Strings sounds | Steven LaGoy | Steven LaGoy | Low | Done | Done | 2026-03-25 14:13 | 2026-03-29 22:23
Story | CP-219 | 11148 | Flyer for play testing | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-03-25 13:56 | 2026-03-29 22:23
Task | CP-228 | 11157 | Adjust daylight cycle | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-03-25 14:14 | 2026-03-30 13:31
Story | CP-144 | 10648 | Race challenges | Steven LaGoy | Steven LaGoy | Low | Done | Done | 2026-01-14 13:31 | 2026-04-08 12:27
Story | CP-141 | 10645 | Parkour challenges | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-01-14 13:31 | 2026-04-08 12:27
Story | CP-257 | 11222 | Print and distribute playtesting flyers | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2026-04-01 16:14 | 2026-04-04 15:21
Story | CP-258 | 11223 | Post playtesting flyers |  | Steven LaGoy | Medium | Done | Done | 2026-04-01 16:14 | 2026-04-04 15:21
Task | CP-232 | 11193 | Add teleport zone to mountain parkour | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:48 | 2026-04-01 15:48
Task | CP-233 | 11194 | Adjust mountain parkour pillar geometries | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:48 | 2026-04-01 15:48
Task | CP-234 | 11195 | Adjust teleport zone for beach parkour | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:48 | 2026-04-01 15:48
Task | CP-235 | 11196 | Add button to center camera view on player look direction | Harrison Niswander | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:49 | 2026-04-01 15:49
Story | CP-229 | 11158 | In-Game Map | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-03-25 14:18 | 2026-04-01 16:11
Story | CP-203 | 10963 | Post Process volume to improve nighttime lighting | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2026-02-25 13:56 | 2026-04-08 10:55
Task | CP-236 | 11197 | Add in-game world map | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:49 | 2026-04-01 15:49
Task | CP-237 | 11198 | Fix daytime cycle lengths | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:49 | 2026-04-01 15:49
Task | CP-238 | 11199 | Balance difficulties of existing race challenges | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:49 | 2026-04-01 15:49
Task | CP-239 | 11200 | Add collision box for doors / passages which always open them | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:50 | 2026-04-01 15:50
Task | CP-240 | 11201 | Add note rewards to existing puzzles | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:50 | 2026-04-01 15:50
Task | CP-241 | 11202 | Spread out pads for crystal puzzle | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:50 | 2026-04-01 15:50
Task | CP-242 | 11203 | Add more crystals to cave | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:50 | 2026-04-01 15:50
Task | CP-243 | 11204 | Fix geometry of bush foliages | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:51 | 2026-04-01 15:51
Subtask | CP-245 | 11207 | Button prompt for in-game map | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:51 | 2026-04-01 15:52
Subtask | CP-246 | 11209 | Button prompt for pause screen | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:51 | 2026-04-01 15:52
Subtask | CP-247 | 11211 | Percussion puzzle button prompts | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:52 | 2026-04-23 12:37
Subtask | CP-248 | 11213 | Brass puzzle button prompts | Zack McGill | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:52 | 2026-04-23 12:38
Task | CP-249 | 11214 | Fix geometries of boats for castle dock parkour | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:52 | 2026-04-01 15:52
Task | CP-250 | 11215 | Fix collision for marshland trees | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:53 | 2026-04-01 15:53
Story | CP-253 | 11218 | Reinforce theming of areas with instrument-coded objects, plants, etc |  | Steven LaGoy | Medium | To Do |  | 2026-04-01 15:54 | 2026-04-23 12:38
Task | CP-254 | 11219 | Fix slow sprint acceleration issue | Steven LaGoy | Steven LaGoy | Medium | Done | Done | 2026-04-01 15:54 | 2026-04-01 15:54
Story | CP-126 | 10531 | Polish the UI and add settings | Steven LaGoy | Zack McGill | Medium | Done | Done | 2025-11-19 13:36 | 2026-04-01 16:10
Task | CP-218 | 11115 | Fix menus and settings | Steven LaGoy | Steven LaGoy | Highest | Done | Done | 2026-03-16 13:57 | 2026-04-01 16:10
Story | CP-255 | 11220 | Create playtesting flyer | Logan Faulstich | Steven LaGoy | Highest | Done | Done | 2026-04-01 16:13 | 2026-04-01 16:13
Task | CP-256 | 11221 | Get playtesting flyer approved | Steven LaGoy | Steven LaGoy | Highest | Done | Done | 2026-04-01 16:13 | 2026-04-01 16:13
Story | CP-230 | 11159 | Add saving / loading / unstuck menu options | Steven LaGoy | Steven LaGoy | High | Done | Done | 2026-03-25 14:32 | 2026-04-08 12:26
Story | CP-263 | 11260 | Itch.io |  | Steven LaGoy | Low | To Do |  | 2026-04-08 13:07 | 2026-04-23 12:38
Subtask | CP-264 | 11262 | Show affordable door based on collected notes | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2026-04-08 17:30 | 2026-05-04 21:50
Subtask | CP-265 | 11264 | Show spent notes collecting in center of island | Ricardo Saldana | Steven LaGoy | Medium | Done | Done | 2026-04-08 17:30 | 2026-05-04 21:50
Subtask | CP-266 | 11266 | Complete area cutscene: color mechanic + door locks | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-04-08 17:31 | 2026-05-04 21:50
Subtask | CP-267 | 11268 | Game intro cutscene | Logan Faulstich | Steven LaGoy | Medium | Done | Done | 2026-04-08 17:31 | 2026-05-04 21:50
Story | CP-270 | 11271 | Studio & Game Website |  | Steven LaGoy | Low | In Progress |  | 2026-04-08 17:35 | 2026-04-28 14:02