## Sheet1
Play Tester # | Name (with consent) | Date | Team Member Observer | Experience in Gaming (0-5) | Area of concern | Observation from Player | Recommendation from Team | Done?
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Opening File | Windows warning appeared when opening the .EXE file | Look into obtaining .EXE file credentials for Windows
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Settings Menu | Settings menu opens but has not content inside the sub-categories | Look into bug fixing the settings menu | Yes
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Percussion Zone | 2x2 Puzzle was eventually found by player, and 3x3 and 4x4 were harder to find | Place signs or create opening cutscenes to show where the puzzles are located | Yes, added in-game map with POI markers
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Percussion Zone Parkour | Player was teleporting strangely around the 2x2 puzzle due to the teleport box located at the ocean parkour area | Tweak the teleport box for the percussion ocean parkour | Yes
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Crystals Zone | Player got the crystals puzzle concept easily, but took a minute to figure out the rules of the puzzle in the beginning | Add simple instructions near the entrance, or create tip pop-ups for UI | Yes, infostone added to explain puzzle
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Crystals Zone Parkour | Player obtained all music notes, but had slight trouble moving around the parkour assets and using the sprint mechanic | Look into further tweaking the sprint mechanic, it has a slow startup making some parkour harder | Yes
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Castle Zone | Grass and small foliage have collision enabled, resulting in the player bobbing up and down when walking | Check collision for small foliage around the map | Yes, collision disabled for small foliage
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Castle Wall Parkour | Player was not able to obtain the music note located on the castle wall corner near the percussion zone | Add assets to help player with parkour | Yes, changed asset geometry
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Castle Zone | Foliage (or tree) clipping through castle wall by the music note hidden behind fences | Check for foliage clipping | Could not recreate
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Forest Zone | Player had trouble finding where the puzzle was located | Add signs or creating cutscenes to show player where the puzzles are located | Yes, in-game map
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Swamp Zone | Player was bumping their head into the tree models, resulting in them gettting stuck | Check collision for trees around swamp zone | Yes, Modified collision geometry
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Percussion Zone | Player had trouble immediately understanding mouse controls, and would lock themselves out without a mouse | Add control symbol on sign nearby. Check blueprint for mouse control bugs
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Percussion Zone | Player did not notice the hints located on the tree until team member told them | Add opening cutscene to show players the hint nearby
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Percussion Zone | Drums are not aligning with their axis when being swapped around, especially on 3x3 and 4x4 | Check drum blueprint for rounding errors | Yes, dums always go to their final positions and cannot be interrupted
1 | Drew Faulstich | 2026-03-13 | Logan | 5 | Percussion Zone | Took at least a few minutes to solve the 3x3. Took at least ten minutes to solve the 4x4. | Make the 3x3 starting layout easier? Possibly change the picture on top to make each drum easily identifiable.
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Opening File | Windows warning appeared when opening the .EXE file | Look into obtaining .EXE file credentials for Windows
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Crystals Zone | Crystals Puzzle concept was not obvious at first. Player got confused with the music note in the corner being the puzzle reward. Did not finish the puzzle on first go. | Add beginning cutscene or simple instruction signs nearby | Yes, infostone added to explain puzzle
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Parkour | Sprint mechanic was harder to use for player in parkour. Sprint would have a slower startup time | Possibly tweak sprint mechanic | Yes
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Swamp Zone | Player was bumping their head into the tree models, resulting in them gettting stuck | Check collision for trees around swamp zone | Yes, Modified collision geometry
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Swamp Zone | Player got stuck in a death loop when jumping on swamp puzzle balls, pushing them into the ocean | Add a Get Player Unstuck button to menu
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Game Session | Lost progress for puzzles and music notes when player did a soft game session restart | Work on player save settings | Yes
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Percussion Zone | Had trouble finding the 2x2 puzzle | Add beginning cutscene or simple instruction signs nearby | Added a path to the first percussion puzzle
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Percussion Zone | Player got confused by music notes falling from the percussion puzzle completion, thinking they were collectable music notes | Change color of music notes in trees
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Crystal Zone | Player was stuck and confused when puzzle locked up (player stepped off the button too early) | Tweak timing for button mechanic in crystal puzzle | Yes
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Crystal Zone | Player was impressed by crystal zone cutscene | Great job team 😁
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Crystal Zone | Player was confused when crystal puzzle starting the last sequence again after solving it | Add a restart mechanic for puzzle
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Forest Zone | Team member noticed color and texture was gone from many trees in the area | Check forest zone foliage for texture bugs | Could not recreate
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Percussion Zone Parkour | Player tripped the percussion zone parkour teleport box from the swamp zone wall | Check percussion zone parkour teleport box | Yes
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Percussion Zone | Player forgot which spot the empty drum should be located | Add a texture to the floor signalling the empty spot
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Percussion Zone | Player wanted to reset the puzzle while mid-puzzle | Add a reset button nearby to reset puzzle
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Swamp Zone | Player softlocked themselves, getting stuck in foliage around the bamboo wall near the corner of the crystal zone and the middle of the island | Internally check for stuck points with foliage and assets on map
2 | Will Kingston | 2026-03-13 | Logan | 3.5 | Swamp Zone | Player was able to walk around wall near outside beach from the percussion zone to swamp zone | Check invisible walls | Yes
3 | Brock Fuller | 2026-03-09 | Steven |  | Mountain parkour challenge | When the player falls, it is possible to get stuck or end up in an unexplored area. | Add a teleport zone to the mountain parkour challenge, which returns the player to a checkpoint when they fall | Yes
3 | Brock Fuller | 2026-03-09 | Steven |  | Mountain parkour challenge | The geometries of some pillar objects, especially right at the start, make it easy to slide off the platforms | Change the geometries to make this less likely / impossible to happen | Yes
3 | Brock Fuller | 2026-03-09 | Steven |  | Percussion puzzle | The player must double click on drum heads to move them in the puzzles | Allow input like single clicks, and directional inputs from the keyboard
3 | Brock Fuller | 2026-03-09 | Steven |  | Percussion puzzle | The reference image is easy to miss, and difficult to view while doing the puzzle | Make the image larger, and perhaps illuminated. Allow the player to leave the puzzle and/or use a special key to see the reference image | Yes
3 | Brock Fuller | 2026-03-09 | Steven |  | Percussion puzzle | The texture of the drum heads places a little bit of white on the edges of each section of the image. This can be a little confusing when trying to line up images | Alter the image textures on drum heads
3 | Brock Fuller | 2026-03-09 | Steven |  | Music | Most of the music loops are only a few minutes long. This can lead to listening fatigue when in an area for more than a few loops | Lengthen the music tracks and add more variation
3 | Brock Fuller | 2026-03-09 | Steven |  | Forest parkour challenge | The teleport zone is rather sensitive and some of the jumps bring players too close to it, especially at on the first few jumps | Make the start of the challenge course more obvious, raise the platforms further out of the water, and fix the geometry of the small islands | Yes
3 | Brock Fuller | 2026-03-09 | Steven |  | Percussion puzzle | The tutorial 2x2 puzzle is somewhat out-of-the way, while the hardest puzzle is near the main path. Players are more likely to find the hardest puzzle first | Choose new locations for the different sizes of puzzles so the player is more likely / forced to find the tutorial puzzle first
3 | Brock Fuller | 2026-03-09 | Steven |  | Doors and Bridges | Moving objects push the player as they are opening, especially when approached from a side angle. Possible to get stuck | If doors only open during cutscenes, this is not a problem. Otherwise, increase the size of the open collision box
3 | Brock Fuller | 2026-03-09 | Steven |  | Woodwinds Castle Town | It is unclear how players are intended to enter the farm area | Make a more visible gate for players to enter through
3 | Brock Fuller | 2026-03-09 | Steven |  | Player camera controls |  | Add a button to center the camera on the direction the player is facing, especially if the player is using a controller | Yes
3 | Brock Fuller | 2026-03-09 | Steven |  | Map exploration | For new players, it is easy to lose orientation and difficult to get an idea of where in the world one is located. | Add an easy-to-access map showing the whole world. Color code different areas and add signs directing players to each area and POI | Map done
3 | Brock Fuller | 2026-03-09 | Steven |  | Collection challenges | This play tester found collecting notes very compelling | Consider adding more collectable notes | Yes
3 | Brock Fuller | 2026-03-09 | Steven |  | Doors on houses / buildings | It is not clear which doors are openable and which are not. | For doors which cannot be opened (on houses etc), add planks or blockages to the door when applicable. Having NPCs around helps this too
3 | Brock Fuller | 2026-03-09 | Steven |  | Daytime cycle | The daytime cycle did not work through this play testing session | Make the daytime cycle run | Yes
4 |  | 2026-03-29 | Steven |  | Race challenges | Jungle race challenge is challenging | Add a few more seconds to the timer | Yes
4 |  | 2026-03-29 | Steven |  | Strings puzzle | Pick up / drop vine keys may conflict with movement keybinds | Key to pick up / place key needs to be customizable
4 |  | 2026-03-29 | Steven |  | Strings puzzle | Direction of movement when in puzzle feels "opposite" | Align movement directions with camera facing direction
4 |  | 2026-03-29 | Steven |  | Castle area | Little temple thing looks like it should do something | Add an NPC quest or storyline involving the little temple
4 |  | 2026-03-29 | Steven |  | Camera collision | Camera glitches through the ground | Check camera settings for what is causing this behavior. Look at similar camera systems in other games to compare
4 |  | 2026-03-29 | Steven |  | Race challenges | Path markers do help show where to go
4 |  | 2026-03-29 | Steven |  | Doors | Possible to get stuck behind an unpurchased door, unclear to players why it is not opening | Ensure players are not able to get behind an unopened door, or add another collision area that ALWAYS opens the door | Yes
4 |  | 2026-03-29 | Steven |  | Brass puzzle | Balls look like "apples"
4 |  | 2026-03-29 | Steven |  | Percussion puzzle | Clicked and dragged to move the drums | This still works, but consider putting "Click on a drum next to the empty space to move it" text on screen
4 |  | 2026-03-29 | Steven |  | Percussion puzzle | Position of drums does not save / load | Add puzzle drum positions to saved variables for this puzzle
4 |  | 2026-03-29 | Steven |  | Percussion puzzle | Clicking drums too rapidly causes them to end up in strange positions | Make sure the drums always go to a final defined position before stopping
4 |  | 2026-03-29 | Steven |  | Percussion puzzle | Some funny business with the mouse appearing / disappearing when entering and leaving puzzle view | Investigate
4 |  | 2026-03-29 | Steven |  | Note collectables | Not properly showing on the HUD | Fix note collectables HUD | Yes
4 |  | 2026-03-29 | Steven |  | Percussion puzzle | Needs to actually give notes for completion | Add a number of notes given for completing the puzzle | Yes
4 |  | 2026-03-29 | Steven |  | Houses and doors | Walked up to several unopenable doors in the village / forest | Put locks, "Do not disturb" signs
4 |  | 2026-03-29 | Steven |  | Foliage | Some ferns still have collision | Remove the collisions from ferns in front of forest area | No
4 |  | 2026-03-29 | Steven |  | Keys puzzle | Why it green? | Make it not green | No
4 |  | 2026-03-29 | Steven |  | Keys puzzle | Very easy to accidentally step on the farthest left and right crystal pads | Spread the pads out just a little more | Yes
4 |  | 2026-03-29 | Steven |  | Keys puzzle | Needs to actually give notes for completion | Add a number of notes given for completing each stage, and the whole puzzle | Yes
4 |  | 2026-03-29 | Steven |  | Keys puzzle | Cutscene feels a little bare without the colors and with crystals only playing pattern once | Cutscene should play a song
4 |  | 2026-03-29 | Steven |  | Keys cave | Wondered why there was just one small yellow crystal | Add more crystals around | Yes
4 |  | 2026-03-29 | Steven |  | Daytime cycle | Days and nights are very short | Lengthen the daytime cycle | Yes
4 |  | 2026-03-29 | Steven |  | Mountain parkour challenge | Takes time to get from top of mountain to bottom after completion | Add teleporter from end to start and vice versa once complete | Yes
4 |  | 2026-03-29 | Steven |  | Debug | Adding notes one at a time with the debug key is tedious | Button for giving like 100 notes | Yes
4 |  | 2026-03-29 | Steven |  | Foliage | Hard to jump on top of bushes due to their sloped hitbox | Bushes should have more of a box collision | Yes
4 |  | 2026-03-29 | Steven |  | Tire swing in forest | Ran and jumped at the tire swing hoping to go through it. | Allow players to jump through the swing, or make some special interaction (low priority)
4 |  | 2026-03-29 | Steven |  | Race challenges | The timer for races doesn't clearly communicate what it is counting | Label time as seconds, put a clock beside the numbers, etc
4 |  | 2026-03-29 | Steven |  | Race challenges | Green and red start / ending pads can be unclear. Returned to the green pad instead of red one | Clearly separate the start and ending pads, use a checkered marker for the ending zone
4 |  | 2026-03-29 | Steven |  | Game world | Easy to get lost in an area and not know which direction something is in | Add a map | Yes
5 | kiyazo | 2026-03-31 | Steven |  | Game Packager | Packaged game does not run
5 | kiyazo | 2026-03-31 | Steven |  | Installer | Installer fails to install game
5 | kiyazo | 2026-03-31 | Steven |  | Website | Website link to installer is broken
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Game Volume | Must use Windows audio manager, in-game sliders aren't visible | Fix settings screens | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Shaders and gamelook | "Looks awfully pixelated" | Revert whatever caused this
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Percussion puzzle | Drums end up in incorrect positions | Make sure the drums always go to a final defined position before stopping | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Percussion puzzle | Not always clear that you should look at the image first
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Percussion puzzle | Every other time, the cursor is not appearing when accessing the puzzle view
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | In-game map | Not obvious how to access the map | Add a button prompt in the corner of the screen, "Map (Tab)" | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Parkour | Runs off the side of little islands before there's a chance to jump | Add coyote time | Out of scope
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Sprinting | "Sprinting feels unresponsive" | Find why character takes a while to speed up and fix | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Brass puzzle | Not clear which buttons to use for the puzzle |  | Yes, added button prompts
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Music | Loud
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Controls | Not clear how to control things | More button prompts | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Keys puzzle | Leaving pads too early | Remove pause between stages when all pads turn white | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Keys puzzle | Pads double trigger and count a wrong sequence |  | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Mountain parkour challenge | Liked "Return to start" pad at top of mountain
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Notes | Sometimes looked like note should have been collected but it wasn't |  | Yes, fixed bug in save function
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Strings puzzle | Looking in different directions changes what WASD does | Make movement directions always the same | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Dock parkour challenge | Jump from first boat is difficult because the boat redirects movement | Change collision of boats | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Parkour challenges | Add an animation when parkours are complete | Animation for completing each parkour challenge
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Race challenges | Hard to know what direction to run in in the first place | Give a countdown to actually starting (IE 3 2 1 GO) | Allowed stepping in starting zone again to restart timer
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Farm in castle area | Could not find way in and had to be shown the gate |  | Yes, Changed gate to be more obvious
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Center island bridges | Not as responsive as previously for whatever reason
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Gameplay experience | Decent amount of time, would spend $15 for this game
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 |  | Compared to "Human Fall Flat"
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 |  | Ended up stuck in the rivers
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Daytime cycle | Night looks good, easy to see most stuff (except for balls in brass puzzle) | Figure out how to make balls visible at nighttime | Yes, Added PPV that makes nightime much brighter
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Invisible walls | Invisible walls block areas that are unlocked | Remove invisible walls when an area is unlocked
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Feedback sound effects | Sound effect for drum moving
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 | Mountain parkour challenge | One particular step jump is hard to do | Lower that platform just a touch | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 |  | Enjoyed the sliding puzzles most, followed by keys | Good job L+R!
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 |  | Trees in marshland area stop you moving a lot | Fix the hitboxes | Yes
6 | Jacob Heffelmire | 2026-04-01 | Steven | 4 |  | Liked steps glowing on ground, lighting in general
7 | maomao | 2026-04-01 | Steven |  | Center island bridges | Strange behavior with going up and down without animations, do not respect puzzle completion |  | Yes
7 | maomao | 2026-04-01 | Steven |  | Percussion puzzle | Movement animations are stopped when clicking another drum |  | Yes
7 | maomao | 2026-04-01 | Steven |  | Percussion puzzle | Mouse input needs to be ignored when the camera animations are playing
7 | maomao | 2026-04-01 | Steven |  | Movement | "Feels airy" with the animation | Try adjusting gravity | Yes
7 | maomao | 2026-04-01 | Steven |  | Brass puzzle | Something funny happened with the camera not moving
7 | maomao | 2026-04-01 | Steven |  | Brass puzzle | Orange and yellow brass colors look similar
7 | maomao | 2026-04-01 | Steven |  | Saving and loading | Many of the new notes and puzzles are not being saved |  | Yes, fixed bug in save function
7 | maomao | 2026-04-01 | Steven |  | Rocks wall | Possible to get on top of wall and run into invisible wall |  | Changed landscape a bit. Not considered major issue
7 | maomao | 2026-04-01 | Steven |  | Doors | Doors which don't have locks are still waiting for the lock animation to play | Make doors which don't have a lock skip the animation timeline | Yes
7 | maomao | 2026-04-01 | Steven |  | Keys puzzle | Not clear what to do when all pads light up with victory noise | Skip the stage between levels that requires stepping on a pad again | Yes
7 | maomao | 2026-04-01 | Steven |  | Random stump in jungle area | Looks like a watering can but it doesn't do anything | Just remove that one foliage | Yes
7 | maomao | 2026-04-01 | Steven |  | Strings puzzle | Movement depends on camera direction and is difficult to map to the keys | Make the movement always the same in the puzzle area | Yes
7 | maomao | 2026-04-01 | Steven |  | Keys puzzle | Puzzle gives a lot of notes | Reduce the reward amount for this puzzle | Yes
7 | maomao | 2026-04-01 | Steven |  | Collectable notes | Note on the castle wall and in the farm was randomly already collected | Might be some strange save / load behavior | Yes, fixed bug in save function
7 | maomao | 2026-04-01 | Steven |  | Crystal foliage | Crystals don't have collision | Add collision | Yes
7 | maomao | 2026-04-01 | Steven |  | Sequence break | Possible to get behind mountain from brass to keys and vice versa | Create a new wall around the back of the mountain, or make it impossible to get between the sides | Yes
7 | maomao | 2026-04-01 | Steven |  | Sequence break | Might be possible to get between percussion and brass over the ocean | Extend walls | Yes
7 | maomao | 2026-04-01 | Steven |  | Sequence break | Very easy to get between percussion and brass over the lake | Extend walls | Yes
7 | maomao | 2026-04-01 | Steven |  | Race challenges | Not possible to reset the time unless you step on the ending pad | Stepping on green pad while race active should reset the time | Yes
7 | maomao | 2026-04-01 | Steven |  | Race challenges | State is not influenced by saving and loading | Make completion of race challenges a tracked variable for saving and loading
7 | maomao | 2026-04-01 | Steven |  | Brass area | Possible to end up in a teleport loop by standing on a valve or ball and falling in the river | Add a teleport area / areas inside the river that tp to the center of the area
8 |  | 2026-04-02 | Steven |  |  | This playtester was a younger user, not as familiar with keyboard and mouse
[5 empty] | Parkour challenges | Took some time to get used to pressing 3 buttons at once, to sprint and jump
[5 empty] | Doors / Progression | Got very fixated on the door to the castle area
[5 empty] | In-game map | Was not sure from the in-game map where the doors to new areas are | Add markings for the doors on the map
[5 empty] | Saving and loading | Collected notes disappeared after saving / loading | Save number of held notes in save information | Yes, fixed bug in save function
[5 empty] | Strings puzzle | Seems not every vine can be picked up first, some strange behavior with placing them
[5 empty] | Keys puzzle | Sometimes stepped on a pad twice, correct pads were considered incorrect | A pad should not trigger two times in a row | Yes, fixed issue with timestep
[5 empty] | In-game map | Returned to completed puzzles several times based on their stars on the map | Make the stars change visually when a puzzle is complete
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Opening File | Windows warning appeared when opening the .EXE file | Look into obtaining .EXE file credentials for Windows
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Settings Menu | Settings menu opens but has not content inside the sub-categories | Look into bug fixing the settings menu | Yes
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Settings Menu | Player could not press escape again to exit menu | look into settings menu | Yes
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Player Character | Momentum feels weird to player | player momentum could be updated if this is agreed on | Yes
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Percussion Zone | Player mentioned issue with barrels being highlighted in the distance | update in interaction logic
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Jungle Zone | Left middle side of the fence removed top down camera, camera controls were skewed, door to caves was already down/nothing there | look into doors logic and setting hard-coded camera controls for jungle puzzle | Yes
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Swamp Zone | PLayer would like audio feedback on the swamp puzzle | look into adding audio when completing events that are more subtle | The swamp puzzle plays audio for correct and incorrect balls leaving bells. Sounds for correct valves considered distracting / unnecessary
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Swamp Zone | Player would prefer clicking on levers as opposed to using 1 2 3 | Consider adding more collectable notes | Yes
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Gameplay experience | player really enjoyed unlocking color of an area | consider other playtesters preferences or add multiple options
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Forest Zone | Player had trouble finding where the 2x2 puzzle was located | perhaps add more noticeable paths or signs for direction
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Forest Zone | player had 40 music notes but couldnt open door to woodwind town | check on door purchase logic
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Percussion Zone | Player softlocked himself in the tree stump | scale down stump or remove altogether
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Percussion Zone | Player did not notice the hints located on the tree until team member told them | fix lighting, should be pulsing bright to be noticeable
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Percussion Zone | Drums are not aligning with their axis when being swapped around, especially on 3x3 and 4x4 | need to make player unable to click until first sliding drum falls into position | Yes
9 | Quincy Adamski | 2026-04-08 | Ricardo | 3.5 | Percussion Zone | Took at least a few minutes to solve the 3x3. Took at least ten minutes to solve the 4x4. | could make 4x4 optionable or swap with 3x3 | Area completion now requires two puzzles being completed. The door to the brass area only requires two puzzles completed.
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Opening File | Windows warning appeared when opening the .EXE file | Look into obtaining .EXE file credentials for Windows
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Swamp Zone | Interacting with the level did not start the flow of balls down the river | look into marshland puzzle starting logic | Player must press E to start the puzzle. There is an interact prompt for this
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Parkour | Player recommended slightly quicker momentum | player momentum could be updated if this is agreed on | Changing momentum could impact existing parkour puzzles
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Keybinds | Player noticed that M and N mess up the lighting, P and K reset the world | need to disable those in final package
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Game Stats | 20fps 80%gpu 50%cpu intel i7 9750HS 2.6 ghz 16gb ram 6gb vram | optimization could be improved
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Game Session | Game properly saved when saving, exiting, and relaunching. | good work!
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Percussion Zone | door lock and money requirements reappeared and disappeared again after player relaunched the game mid-session | may need added to saving and loading requirements
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Percussion Zone | Player would prefer muted colors as opposed to full grayscale of the environment | can consider our time and plausibility for this change
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Crystal Zone | Player had to make multiple correct attempts for puzzle to recognize their attempt as correct | look into keys puzzle completion logic
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Mountain parkour challenge | Player liked the checkpoints | good work!
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | All Puzzles | The important objects that need color are currently gray which ruin the experience | need to look into color mechanic ppv | Yes
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Forest Zone | Team member noticed color and texture was gone from many trees in the area | may be an asset issue we need to look into | Could not recreate
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Percussion Zone | Player had trouble immediately understanding mouse controls, and would lock themselves out without a mouse until pressing space to jump | could add a tutorial area to better introduce player to game mechancis | Yes
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Percussion Zone | Player forgot which spot the empty drum should be located | maybe set a border around the drums or some placeholder in the empty spot
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Percussion Zone | player mentioned they could move during percussion puzzle | remove player controls same time changing the camera scene
10 | Michael Barrell | 2026-04-08 | Ricardo | 3.5 | Area Completion/Loading | player completion color was reset during loading or relaunching the game, but randomly reappeared color in completed areas
11 | Kaden Vinson | 2026-03-30 | Logan | 5 |  |  | Check invisible walls
12 | Abhi Mulpuri | 2026-03-30 | Logan | 1 |  |  | Check invisible walls
13 | Nathan Potts | 2026-03-30 | Logan |  |  |  | Check invisible walls